## Project Tracker
Task ID | Task | Assigned To | Team | Start Date | Due Date | Priority | Status | Completion % | Milestone | Days Remaining | Delay Status
T001 | Gather Project Requirements | Ananya | UI/UX | 01-Aug-2026 | 03-Aug-2026 | High | Completed | 100% | Planning
T002 | Prepare Project Scope Document | Rahul | Backend | 01-Aug-2026 | 04-Aug-2026 | High | Completed | 100% | Planning
T003 | Create Initial Wireframes | Ananya | UI/UX | 03-Aug-2026 | 06-Aug-2026 | High | Completed | 100% | Design
T004 | Review Wireframes with Team | Priya | UI/UX | 07-Aug-2026 | 08-Aug-2026 | Medium | Completed | 100% | Design
T005 | Finalize Dashboard Design | Priya | UI/UX | 08-Aug-2026 | 12-Aug-2026 | Medium | In Progress | 75% | Design
T006 | Design Mobile Interface | Ananya | UI/UX | 10-Aug-2026 | 14-Aug-2026 | Medium | In Progress | 60% | Design
T007 | Create Database Schema | Karthik | Backend | 03-Aug-2026 | 07-Aug-2026 | High | Completed | 100% | Development
T008 | Set Up Development Database | Karthik | Backend | 06-Aug-2026 | 10-Aug-2026 | High | Completed | 100% | Development
T009 | Develop User Registration API | Rahul | Backend | 08-Aug-2026 | 14-Aug-2026 | High | In Progress | 80% | Development
T010 | Develop Login API | Rahul | Backend | 09-Aug-2026 | 15-Aug-2026 | High | In Progress | 70% | Development
T011 | Develop User Profile Module | Karthik | Backend | 12-Aug-2026 | 19-Aug-2026 | Medium | In Progress | 50% | Development
T012 | Build Login Page | Priya | Frontend | 11-Aug-2026 | 16-Aug-2026 | High | Completed | 100% | Development
T013 | Build Registration Page | Priya | Frontend | 13-Aug-2026 | 18-Aug-2026 | Medium | In Progress | 65% | Development
T014 | Build User Dashboard UI | Arun | Frontend | 15-Aug-2026 | 22-Aug-2026 | High | In Progress | 45% | Development
T015 | Implement Navigation Menu | Arun | Frontend | 16-Aug-2026 | 20-Aug-2026 | Medium | Completed | 100% | Development
T016 | Integrate Login API with Frontend | Rahul | Backend | 17-Aug-2026 | 23-Aug-2026 | High | In Progress | 40% | Development
T017 | Integrate User Profile API | Karthik | Backend | 19-Aug-2026 | 26-Aug-2026 | Medium | Not Started | 0% | Development
T018 | Implement Notification Feature | Rahul | Backend | 20-Aug-2026 | 28-Aug-2026 | Low | Not Started | 0% | Development
T019 | Develop Search Functionality | Arun | Frontend | 18-Aug-2026 | 25-Aug-2026 | Medium | In Progress | 35% | Development
T020 | Perform UI Testing | Meena | QA | 19-Aug-2026 | 23-Aug-2026 | Medium | Completed | 100% | Testing
T021 | Test User Registration | Meena | QA | 21-Aug-2026 | 25-Aug-2026 | High | In Progress | 40% | Testing
T022 | Test Login Functionality | Meena | QA | 22-Aug-2026 | 26-Aug-2026 | High | Not Started | 0% | Testing
T023 | Perform API Testing | Suresh | QA | 23-Aug-2026 | 29-Aug-2026 | High | Not Started | 0% | Testing
T024 | Perform Regression Testing | Suresh | QA | 27-Aug-2026 | 31-Aug-2026 | Medium | Not Started | 0% | Testing
T025 | Fix Login Validation Bug | Rahul | Backend | 20-Aug-2026 | 22-Aug-2026 | High | Blocked | 60% | Testing
T026 | Fix Dashboard UI Issues | Arun | Frontend | 21-Aug-2026 | 24-Aug-2026 | Medium | In Progress | 50% | Testing
T027 | Review Test Results | Ananya | UI/UX | 29-Aug-2026 | 01-Sep-2026 | Medium | Not Started | 0% | Testing
T028 | Prepare User Documentation | Priya | UI/UX | 27-Aug-2026 | 02-Sep-2026 | Low | Not Started | 0% | Deployment
T029 | Prepare Production Environment | Karthik | Backend | 29-Aug-2026 | 03-Sep-2026 | High | Not Started | 0% | Deployment
T030 | Configure Application Settings | Rahul | Backend | 30-Aug-2026 | 04-Sep-2026 | High | Not Started | 0% | Deployment
T031 | Deploy Application to Staging | Arun | Frontend | 02-Sep-2026 | 05-Sep-2026 | High | Not Started | 0% | Deployment
T032 | Conduct User Acceptance Testing | Meena | QA | 04-Sep-2026 | 08-Sep-2026 | High | Not Started | 0% | Deployment
T033 | Resolve UAT Issues | Suresh | QA | 08-Sep-2026 | 11-Sep-2026 | High | Not Started | 0% | Deployment
T034 | Final Deployment | Rahul | Backend | 12-Sep-2026 | 13-Sep-2026 | High | Not Started | 0% | Deployment
T035 | Post-Deployment Verification | Meena | QA | 14-Sep-2026 | 15-Sep-2026 | Medium | Not Started | 0% | Deployment
Formulas:
Days Remaining = [Due Date]-TODAY()
Delay Status = IF([Status]="Completed","Completed",IF([Due Date]<TODAY(),"Overdue","On Track"))

## Lists
Status | Priority | Team | Milestone
Completed | High | Frontend | Planning
In Progress | Medium | Backend | Design
Not Started | Low | UI/UX | Development
Blocked |  | QA | Testing
Deployment